## Cover
TEST PLAN
Project Name |  |  |  | Reviewer | Phạm Hữu Minh Quân
Project Code |  |  |  | Review date | 30/10/2024
Creator | Group 07 |  |  | Approver | Tran Thi Thanh Nga
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy (Link với sheet tên tương ứng) | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Attendance&PayrollSystemSRS.docx |  |  |  | 1
Slides software testing subject |  |  |  | 2019-01-02
Note on E10: - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Leader
2 | Create test design |  |  | Teseter
3 | Create test cases |  |  | Teseter
4 | Create test data |  |  | Teseter
5 | Execute system test |  |  | Teseter
6 | Defects list |  |  | Teseter
7 | Create test report |  |  | Leader
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 30/10/2024 | Test Manager | Customer,PM,Team | This document itself
2 | Test cases | 30/10/2024 | Test Manager | Customer,PM,Team
3 | Defect logs | Updating… | Test Manager | Customer,PM,Team
4 | Test report | Updating… | Test Manager | Customer,PM,Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members do not have much experience in testing software |  | Must plan to study, practice to hone skills |  | 1. Follow the teacher's lesson in class 2. Organize group meetings, help each other improve, cultivate the weak parts
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: steps would have to be done if the risk were to become reality
Note on B41: It can be: - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
Order System
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Smartphone |  |  |  | Standard Fsoft
OS | Window 10
Database | Updating…
Network | Updating…
Software | Google Chrome 86.0.4240.198 |  |  |  | Web browser
Tool | Microsoft Office Excel 2016 Microsoft Office Word 2016
Note on G10: - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | Nguyễn Thị Hoài Thu | Leader | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Danh sách sau quân sự
2 | Nguyễn Ngọc Minh Thư | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Danh sách sau quân sự
3 | Phạm Hữu Minh Quân | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Danh sách sau quân sự
4 | Trần Hoài Nam | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Danh sách sau quân sự
5 | Đỗ Quang Huy | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Danh sách sau quân sự
6
7
8
9
10
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 30/10/2024 | Updating…
2 | Create test design | Updating… | Updating…
3 | Create test case | 30/10/2024 | Updating…
4 | Execute test and log bugs | Updating… | Updating…
5 | Evaluting exit criteria & Test report | Updating… | Updating…
6 | Review | Updating… | Updating…
| Task | Start day from 9/12/2019 | Duration
| Create test plan | #VALUE! | #VALUE!
| Create test design | #VALUE! | #VALUE!
| Create test case | #VALUE! | #VALUE!
| Execute test and log bugs | #VALUE! | #VALUE!
| Evaluting exit criteria & Test report | #VALUE! | #VALUE!
| Review | #VALUE! | #VALUE!
Detail Schedule
Liên kết

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14